## Activities
Priority | Activity | Detailed Activity Description | Who is Responsible for Implementation? | Start Date | End Date | Frequency/ Duration | Plan for Monitoring Implementation and Progress | Who is Responsible for Monitoring? | Resource Needed (1) | Resource Category (1) | Cost Estimate (1) | Quote Included? (1) | Fund Source (1) | Resource Needed (2) | Resource Category (2) | Cost Estimate (2) | Quote Included? (2) | Fund Source (2) | Resource Needed (3) | Resource Category (3) | Cost Estimate (3) | Quote Included? (3) | Fund Source (3) | Resource Needed (4) | Resource Category (4) | Cost Estimate (4) | Quote Included? (4) | Fund Source (4) | Resource Needed (5) | Resource Category (5) | Cost Estimate (5) | Quote Included? (5) | Fund Source (5)
| Parent & Family Engagement | As mandated by ESSA Section 1116 meaningful activities will be conducted to provide the communication and support necessary to assist and build the capacity of all families and staff in planning and implementing effective parent and family involvement activities to improve student academic achievement and school performance. Please refer to the Parent & Family Engagement Plan for specific details. | Title I District PFE Staff, School Administration and School Staff | July 1,2020 | 2021-06-30 | Ongoing throughout the year | Monitoring Documentation Box, eBocx Uploads, parent surveys, onsite visits from Title I diistrict personnel. | Title I District personnel | Communication Tools | Technology |  | no | Title I | Materials | Vendor |  | no | Title I | Staff & Parent Trainings/Conferences | PD |  |  | Title I | Supplies | Materials |  |  | Title I | Conference /Meetings | Travel
4 | Planners | Students will document learning and behavior in planners to share daily with parents. Daily communication between teacher and parent about student's behavior and learning will be documented in the planner. | Administration | 2020-08-01 | 2021-06-30 | Ongoing daily throughout the year | Will be monitored by the teacher daily. | Teacher, Administration | Communication Tools | Materials | 1000 | No | Title I | Planners | Vendor |  | No | Title I
4 | School Uniforms, underpants, shoes, socks, jackets | Students will wear uniforms to school. Uniforms, shoes,jackets, socks and underpants will be provided for those students who are in need. | Administration | 2020-08-01 | 2021-06-30 | Ongoing daily throughout the year as needed | Will be monitored by the socail worker and teachers daily. | Teacher, Administration | Clothing | Materials | 1000 | No | Title I | Uniforms, Jackets, Shoes, Underpants, socks | Vendor |  | No | Title I
4 | Backpacks and school supllies | Students will utilize backpacks to transport their supplies daily to and from school. | Administration | 2020-08-01 | 2021-06-30 | Ongoing daily throughout the year as needed | Will be monitored by the socail worker and teachers daily. | Teacher, Administration | Backpacks and school supplies | Materials | 1000 | No | Title I | Backpacks and school supplies | Vendor |  | No | Title I
4 | Laundry Detergent and Hygiene products | Students/parent will receive laundry detergent and hygiene products as needed. | Administration | 2020-08-01 | 2021-06-30 | Ongoing daily throughout the year as needed | Will be monitored by the socail worker and teachers daily. | Teacher, Administration | Laundry detergent and hygiene products | Materials | 500 |  | Title I | Laundry Detergent and Hygiene Products | Vendor |  | No | Title I
4 | Water | Parents and students will be provided water at conferences and meetings. | Administration | 2020-08-01 | 2021-06-30 | Ongoing throughout the year as needed | Will be monitored by the socail worker and teachers daily. | Teacher, Administration | Water | Materials | 167 |  | Title I | Water | Vendor |  | No | Title I
| Title I Allocation: | [5 empty] | Personnel Requested
| Title I Expenditures | #VALUE!
TSSSA Allocation:
TSSSA Expenditures
Unisig Allocation:
Unisig Expenditures
Other Allocation:
Other Expenditures:
| Total Allocation: | 0
| Total Expenditures: | #VALUE!
| Balance: | #VALUE!

## Responses (hidden)
School | Team | Roles | Need1 | Need2 | Need3 | Need4 | Need5 | Plan1 | Plan2 | Plan3 | Plan4 | Plan5 | Problem | Why1 | Why2 | Why3 | Why4 | Why5 | Previous1 | Previous2 | Previous3 | Previous4 | Previous5 | Goal1 | Goal2 | Goal3 | Problem | Why1 | Why2 | Why3 | Why4 | Why5 | Previous1 | Previous2 | Previous3 | Previous4 | Previous5 | Goal1 | Goal2 | Goal3 | Problem | Why1 | Why2 | Why3 | Why4 | Why5 | Previous1 | Previous2 | Previous3 | Previous4 | Previous5 | Goal1 | Goal2 | Goal3 | Problem | Why1 | Why2 | Why3 | Why4 | Why5 | Previous1 | Previous2 | Previous3 | Previous4 | Previous5 | Goal1 | Goal2 | Goal3 | Problem | Why1 | Why2 | Why3 | Why4 | Why5 | Previous1 | Previous2 | Previous3 | Previous4 | Previous5 | Goal1 | Goal2 | Goal3
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## Consultants (hidden)
Contract with External Consultant
Name of Consultant | Service to be Provided | Contract Amount
Grand Total of Consultant Contracts |  | 0

## Sheet1 (hidden)
Title I | Priority | Title I $ | TSSSA $ | Unisig $ | Other $ | Title I $ | TSSSA $ | Unisig $ | Other $ | Title I $ | TSSSA $ | Unisig $ | Other $ | Title I $ | TSSSA $ | Unisig $ | Other $ | Title I $ | TSSSA $ | Unisig $ | Other $
UniSIG | 0 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
TSSSA | 4 | 1000 |  |  |  | 0
Other | 4 | 1000 |  |  |  | 0
| 4 | 1000 |  |  |  | 0
| 4 | 500 |  |  |  | 0
| 4 | 167 |  |  |  | 0
0
0
0
0
0
0
0
0
Yes | 0
No | 0
0
0
0
0
0
0
0
| #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | Count | $
|  | Title I Total | 5 | #VALUE!
|  | TSSA Total | 0 | #VALUE!
|  | Unisig Total | 0 | #VALUE!
|  | Other Total | 0 | #VALUE!

## Sheet5 (hidden)
Personnel | List without blanks | Personnel | Personnel | Personnel | Personnel
#VALUE! |  | #VALUE! | #VALUE! | #VALUE! | #VALUE!
#VALUE! |  | #VALUE! | #VALUE! | #VALUE! | #VALUE!
#VALUE! |  | #VALUE! | #VALUE! | #VALUE! | #VALUE!
#VALUE! |  | #VALUE! | #VALUE! | #VALUE! | #VALUE!
#VALUE!

## Sheet2 (hidden)
FALSE
Gains
Bottom Quartile Gains
Personnel
PD
Materials
Technology
Vendor
Travel
Other
Yes
No