## Sheet1
Task | Bureau/Program Office | Jan. | Feb. | March | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec.
Title I, Part A: Improving the Academic Achievement of the Disadvantaged
BFEP releases annual guide to calculations | BFEP | bar: Jan.
BFEP mails certified roll forward letters to LEAs | BFEP | bar: Jan.
Certified roll forward amendment period | BFEP | bar: Jan. to March
BFEP releases RFA and opens Title I, Part A application to LEAs | BFEP | March: March 2
LEA submits Title I, Part A program application (reviewed in order received) | BFEP | May: May 1
Program period begins | BFEP | July: July 1
Comparability online reporting | BFEP | bar: Oct. to Nov.
Comparability review and LEA correction period | BFEP | bar: Nov. to Dec.
Deadline for LEAs to meet comparability requirements | BFEP | bar: Jan.
K code amendment period (after October FTE) | BFEP | bar: Oct. to Dec.
BFEP releases final allocations | BFEP | bar: July to Aug.
Title I, Part C: Education of Migratory Children
BFEP releases summer program allocations to LEAs | BFEP | bar: Feb.
BFEP releases RFA and opens Migrant Education Program application to LEAs | BFEP | bar: April
BFEP disseminates summer migrant program evaluation template to LEAs | BFEP | bar: April
LEAs submit Migrant Education Program application | BFEP | June: June 1
BFEP disseminates 2020-2021 Certificate of Eligibility (COE) forms to LEAs | BFEP | bar: June
Program period begins | BFEP | July: July 1
BFEP disseminates Annual Evaluation Report template to LEAs | BFEP | bar: Aug.
BFEP collects Migrant Summer Program evaluation reports | BFEP | bar: Sept.
BFEP collects annual evaluation report results | BFEP | bar: Oct.
BFEP collects summer migrant program survey results from LEAs to inform summer allocations | BFEP | bar: Nov.
Title I, Part D: Prevention and Intervention Programs for Children and Youths Who Are Neglected, Delinquent, or At Risk
BFEP releases and opens Neglected and Delinquent Youth program application RFA to LEAs | BFEP | bar: April
LEA submits mid-year report | BFEP | bar: March
LEA submits final report | BFEP | bar: Sept.
LEA submits Neglected and Delinquent Youth program application | BFEP | June: June 1
Program period begins | BFEP | July: July 1
LEA submits Survey 9/annual caseload count | BFEP | bar: Dec.
LEA submits final edits Survey 9/annual caseload count | BFEP | bar: Jan.
Title V, Part B, Subpart 2: Rural and Low-Income School Program
BFEP releases and opens Rural and Low Income Schools program application RFA to LEAs | BFEP | bar: April
LEA submits Rural and Low Income Schools program application | BFEP | June: June 1
Program period begins | BFEP | July: July 1
TitIe IX, Part A: Education for Homeless Children and Youths
LEA submits 2018-2019 EHCY (Education of Homeless Children and Youth) End-of-Year Report for previous year, if applicable | BFEP | bar: Jan.
LEA submits completed 2019-2020 EHCY Sub-grant Progress Report for current year, if applicable | BFEP | bar: Feb. to March
BFEP releases RFA and opens Title IX, Part A application to LEAs | BFEP | bar: May
LEA completes and submits 2020-2021 EHCY Sub-grant application, if applicable | BFEP | June: June 12
Program period begins | BFEP | July: July 1
LEA and program office participate in Statewide Homeless Liaisons' conference calls | BFEP | bar: Jan.; March; Aug.; Nov.
BFEP Monitoring Schedule
BFEP releases monitoring workpapers (for previous grant cycle) | BFEP | bar: Aug.
BFEP notifies LEA of monitoring status | BFEP | Aug.: Aug. 15
LEA completes monitoring uploads and workpapers in online system | BFEP | Sept.: Sept. 30
Monitoring review period | BFEP | bar: Oct. to Nov.
BFEP conducts onsite and desktop monitoring | BFEP | bar: Jan.; Nov. to Dec.
BFEP Survey Data Dates
Survey 2 reporting/verification period | BFEP | bar: Oct. to Dec.
Deadline to amend Survey 2 data | BFEP | bar: Dec.
Survey 3 reporting/verification period | BFEP | bar: Feb. to April
Deadline to amend Survey 3 data | BFEP | bar: April
Survey 5 reporting/verification period (July- Mid August: weekly; Mid August- October: biweekly) | BFEP | bar: July to Oct.
Deadline to amend Survey 5 data | BFEP | bar: Oct.
Title II, Part A: Supporting Effective Instruction
Title II releases RFA and program application to LEAs | Title II | bar: April
LEA submits Title II, Part A Program application | Title II | June: June 1
Program period begins | Title II | July: July 1
Title II releases Title II, Part A monitoring workpapers to LEAs | Title II | bar: Nov.
Monitoring review period | Title II | bar: Jan.; Dec.
Title II conducts onsite and desktop monitoring | Title II | bar: Jan. to Feb.
Title II releases Title II, Part A final allocations and certified roll forward to LEAs | Title II | bar: Jan.; Dec.
Title III, Part A: English Language Learners
Title III releases Title III, Part A RFA and program application to LEAs | Title III | bar: May
LEA submits Title III, Part A Program application | Title III | June: June 30
Program period begins | Title III | July: July 1
Title III releases Title III, Part A monitoring workpapers to LEAs | Title III | bar: Nov. to Dec.
Title III releases certified roll forward to LEAs | Title III | bar: Jan.; Dec.
Title IV, Part A: Student Support and Academic Enrichment Grants
BSIS releases Title IV, Part A RFA and program application to LEAs | BSIS | bar: March
BSIS release Title IV, Part A program quarterly amendment schedule | BSIS | Aug.: Aug. 15
LEA submits Title IV, Part A program application | BSIS | July: July 31
Program period begins | BSIS | Aug.: Aug. 1
BSIS releases Title IV, Part A monitoring workpapers to LEAs | BSIS | bar: Nov. to Dec.
BSIS releases final allocations to LEAs | BSIS | bar: Aug.
BSIS releases certified roll forward to LEAs | BSIS | bar: Jan.; Dec.
Title IV, Part B: Nita M. Lowey 21st Century Community Learning Centers (21st CCLC)
BFCO Releases 21st CCLC RFP to Public (new LEA and agency recipients) | BFCO | bar: March
BFCO conducts RFP trainings statewide | BFCO | bar: Jan. to Feb.
New LEA and agency recipients submit program application for RFP | BFCO | May: May 15
BFCO releases RFA (existing LEA and agency recipients) | BFCO | bar: May
Existing LEA and agency recipients submit program application for RFA | BFCO | June: June 26
BFCO releases RFP results/funding recommendations | BFCO | bar: June
BFCO conducts budget and technical review of all applications | BFCO | bar: May to July
All project periods begin | BFCO | Aug.: Aug. 1
LEA submits program deliverables | BFCO
BFCO conducts onsite monitoring and compliance visits | BFCO | bar: Jan. to May; Sept. to Dec.
BFCO conducts onsite technical assistance through site visits | BFCO | bar: Jan. to March; Oct. to Dec.
Bureau of School Improvement
LEA submits Turnaround School Supplemental Services Allocation (TSSSA) to district school board for approval | BSI | Aug.: Aug. 1
LEA submits UniSIG budget and district UniSIG Survey (application) to BSI | BSI | June: June 30
LEA submits TSSSA application/plan to BSI Program | BSI | June: June 30
LEA submits instructional rosters as of 8/30 for UniSIG Supplemental Teacher Allocation | BSI/ARM | bar: Aug. to Sept.
UniSIG program period begins | BSI | Sept.: Sept. 1
TSSSA program period begins | BSI | Sept.: Sept. FEFP
UniSIG Supplemental Teacher Allocation program period begins | BSI | bar: Sept.